## WSR Week 28
Account | Project | Importance | Delivery Model | Billing Model | Tower | FTE | Revenue | PM | WSR Publish Status (Y/N) | Health Week 26 | Health Week 27 | Health Week 28 | Client Escalation | Update for the Current week | Plan for next week | Issues/Challenges | Path to Green | Resourcing Status | Current SDLC Phase | SQA Remarks
CALX | CALX Compass | Strategic | Managed | Fixed Bid | Tower 2 |  |  | Vijo Jacob | Y | Red | Red | Red | None | Pending Items - Still awaiting confirmation on the critical showstopper items related to UI component library, CMS and Maps. This has an impact on the overall schedule and scope Customer Connect - Had customer connect with Saad and Asim. Expecting update by 15th Jul and if there are further delays, have to put entire activities on hold. | Discuss with Calx team on the delays and get confirmation on pending items | Delay in getting confirmation on the pending items from Calx/Ministry | Confirmation on the pending items and agree on revised plan | None | Requirement Gathering | Revised SOW with revised scope and estimate shared with customer. Customer signing to be obtained.
New Era Cap | Snowflake Data Team | Critical | Managed | T&M | Tower 1 |  |  | Rajeev Kallumpurath | Y | Amber | Amber | Amber | None | The June deliverables completed successfully with all those crystal reports moved to Production. The team is currently focusing on OLAP reports and Sales Analysis reports to close within mid July along with Power IB Enhancement Requests. The BW reengineering track solution approach being drafted to present to NEC to review and baseline it. | 1) Mapping and ETL Development for dimensions and fact tables for OLAP reports.​ 2) AtScale development for OLAP.​ 3) Data refresh via BW connector and ODBC connector .​ 4) BI Team will be handling the CR raised by users for multiple reports if any.​ 5) OLAP data testing in snowflake layer.​ |  |  |  |  | BCP and Information Security Risk Register not submitted by the project team
Seymour Whyte | Seymour Whyte Connect | Strategic | Managed | Capacity | Tower 2 |  |  | Ashwathy Nair | Y | Amber | Amber | Red | None | * Overall project progress (from Reflections) - 69% * RAG – “RED”, Due to the dependency on the source/target API. API of Equipment Timecard will be made available only towards end of Aug, impacting the project date, * Session for new business flow is planned for 14th July. * Test scenario – AWAITING review comments. Test case preparation is in progress * Note – Requirement “Plug & Play”- Implemented in the current code. * Quarterly NPS Score to be received | * Update the design suggested and complete any work till the APIs are available * Continue build and test case preparation | • the dependency on the source/target API. • SAP APIs are not working which makes most of the modules in BLOCKED status. • Additional business logic and design changes are getting suggested at this stage, which may impact the overall project timeline. | * Updated the risk to the customer as the delay is due to the API at their end. | No Risk - GREEN | Development
Halo | Halo |  | Staff Aug | T&M | Tower 1 |  |  | Srinivasan K R | Y | Amber | Amber | Amber | None | Automation of Fixed income case to test details of calendar, FI Calendar :Search by Underlying asset Manage Auctions: Filter with whitelabel name Calendar Details modal - Income Manage Auctions: Filter the Active Auctions Maintenance of post,pershing and Janney cases HADT-22940 BE : WL override does not send the notification type response HADT-23038 Option to leave the SMA startegy ID blank HADT-22870 Disable Excel Export Button for Whitelabel Master Users on Portfolio & Lifecycle Screens | QA Tasks and Dev Tickets will be assigned by today. | 1. SOW pending 2. Account clousure by end of Oct 2025 | 1. SOW got signed this week 2. Taking steps to project our capabilities and value adds to avoid/extend account closure. | None | Agile - Sprint | Customer wanted to move the team members to their payroll which we declined. Contract extension is for 6 months only and by that time, most probably they will find replacement for our team members
Brandix | Brandix HRMS | Strategic | Managed | Fixed Bid | Tower 2 |  |  | Vijo Jacob | Y | Amber | Amber | Amber | None | Targeting to start HRMS support from 1st August, however prerequisites are still being worked upon and no major progress achieved. This has been informed to Shirmin and expecting a quick resolution. | KT session with schemax and continue understanding the application. | Delay in getting the prerequisties access for application and DB, | Complete pre requisties activities and start support | None | KT
Seymour Whyte | Seymour Whyte HRIS Support | Strategic | Staff Aug | Capacity | Tower 2 |  |  | Ashwathy Nair | Y | Amber | Amber | Green | None | * No new issues reported. * Team changing the API to Reports for the pipeline and doing code optimization * Implementing Primary key change that was requested before. * Review of code for design improvement | Continue to work on any open issues | * Clients choice to move to P2P and put the solution on Hold till Connect project is completed. * The changes to P2P from their end is causing API failures. | * Utilizing the one month support time to optimize the solution proactively * AGreement with client on the API call issues as know issues. | AMBER - Vibin's concerns have been raised to HR. | Support | There is no evidence of customer acceptance for implemented bug fixes, enhancements, or changes to requirements. It is recommended to ensure that acceptance confirmations from the customer are properly recorded and maintained for all such deliveries.
Akumin | Akumin Support |  | Staff Aug | T&M | Tower 1 |  |  | Srinivasan K R | Y | Green | Amber | Amber | None | No Updates as the Resource was on Leave for the complete week | Client will assign tickets during US Hours | We had informed the client earlier that our prime resource would be on leave for a week and had arranged for a backup resource to ensure continuity of support during this period. However, the credentials for the backup resource have not yet been provisioned. We have been consistently following up on this request, but unfortunately, we have not received the required access details yet. | As the Prime Resource is back from Leave and hence he will start taking care of AkuminOne Project. | None | As it is a support project tickets are assigned in Invanti Tool by customer.
New Era Cap | Integrations Stream |  | Managed | T&M | Tower 1 |  |  | Rajeev Kallumpurath | Y | Green | Green | Green | None | The Smaregi integration work includes ongoing analysis for error logging in the Product Create API, implementation of a retry mechanism for failed requests to the BW web service. For the JP Retail Dashboard, the updated 4-Wall Operating Profit calculation has been successfully deployed to production. In the Geodis Mexico project, incorrect delivery number mappings have been identified for both inbound and outbound payloads, with fixes in progress. In the Supplier Portal –SAP report details for the packing export enhancement have been shared. 22 Zendesk tickets has been closed | 1) Middleware Migration Project - Continue with the development task.​ 2) 47 KTN EMEA Wholesale Expansion - dev testing will be in-progress​ 3) Smaregi Integration and Supplier Portal - Product Create API [Logging and Retry]​ 4) Geodis Mexico - Return Order and B2C Inventory Comparison Report​ 5) Production Support - Support activities to be handled. |  |  | Interviews for the roles Sr. Net Developer & .Net Developer are in progress. |  | BCP and Information Security Risk Register not submitted by the project team
New Era Cap | eCommerce |  | Managed | T&M | Tower 1 |  |  | Rajeev Kallumpurath | Y | Green | Green | Green | None | The main priority for the team was working on Submarine items, which received much of the focus and effort. EMEA Returns and SHOPIFY POS stories were the other priority items planned this week. The team continued to provide production support for SOFIA, as well as for the ROAL application, maintaining system stability and addressing any critical issues. ​ | 1) Submarine Bugs​ 2) SOFIA EU UK US MX PROD Support​ 3) SHOPIFY POS​ 4) ROAL Application Support​ 5) ADA Tasks​ 6) SOFIA EMEA Returns |  |  |  |  | BCP and Information Security Risk Register not submitted by the project team
GBM | QIB | Critical | Managed | Fixed Bid | Tower 2 |  |  | Vijo Jacob | Y | Amber | Green | Green | None | Revised plan shared with customer for review. Middleware development activities completed and reviews also in place. | Get confirmation on plan and review Data Masing and Threat protection. | • SAP APIs are not working which makes most of the modules in BLOCKED status. |  | None | Execution
GTA | GTA |  | Staff Aug | Capacity | Tower 2 |  |  | Vijo Jacob | Y | Amber | Green | Green | None | Cluster Upgrade - Received signed addendum. Started cluster upgrade activities related to environment readiness from 7th Jul. Support - HSBC RCS provided and supported QNB and mainteance activities | Continue with Cluster Upgrade activities. Dukhan Bank Certificate renewal |  |  | None | Execution
Brandix | Brandix | Strategic | Staff Aug | T&M | Tower 2 |  |  | Vijo Jacob | Y | Amber | Green | Green | None | SE and SRE activities in progress as planned. Senior DBA - Interviews in progress | Continue activities for SE and SRE as per sprint commitments |  |  | Senior DBA - Customer has rejected Taruns profile. Working on other profiles | Execution
New Era Cap | Product Builder |  | Managed | T&M | Tower 1 |  |  | Rajeev Kallumpurath | Y | Green | Green | Green | None | Sprint 7 – QA release deployed, and smoke tested, which includes the 'Duplicate Product Check' feature. Production release is planned for next week.​ Revised Logo Placement Experience – BRD analysis and wireframe review in progress. Technical architecture is scheduled to be finalized on July 17th. | 1) Sprint 7 – QA and Production release is planned.​ ​2) Revised Logo Placement Experience – Based on the wireframe, planning to work on React component(storybook and other page level component) creation for the frontend page design. |  |  |  |  | BCP and Information Security Risk Register not submitted by the project team
New Era Cap | Architecture |  | Staff Aug | T&M | Tower 1 |  |  | Rajeev Kallumpurath | Y | Green | Green | Green | None | 1) The SailPoint configuration audit is currently in progress.​ 2) Dev Support for Aftership Completed and dev support Product builder is in Progress.​ 3) Dev support for Inventory Comparison Report Mexico and Smaregi are in Progress.​ 4) Architecture tasks of Bloomberg Migration is in Progress and Submarine HotMarket fulfillment changes have been complete​d | 1) Architecture – GCP - Revised Logo Placement Experience​ 2) Smaregi – Development support​ 3) Azure vulnerability Fixes​ 4) Performance Monitoring – SAP HANA Admin Tasks​ 5) Dev Support-Inventory Comparison Report Mexico​ 6) Architecture-Bloomberg Migration | Due to recent budget reductions, a few resources have been released from the project. Consequently, tasks related to the 47 Brand initiative are currently on hold. |  | Resource planning is underway for a newly created Architect role. |  | BCP and Information Security Risk Register not submitted by the project team
New Era Cap | SharePoint Migrations |  | Staff Aug | T&M | Tower 1 |  |  | Rajeev Kallumpurath | Y | Green | Green | Green | None | Global Intranet now accessible; IT using it to publish training data; handholding on site build in progress. NPI still in UAT. AI/Copilot strategy launched. Migration continues but with smaller sites. | 1) Negotiate for HR & Internal Comms go-live once ready; handhold until then and afterwards​ 2) Legal, Finance, Facilities; sites need polishing and then socialization & training​ 3) 4 weeks: plan migration of the heavy users and their 6K content items​ 5) Integrate NPI feedback and plan launch as panel sees fit​ 6) Trim file versions to save space in tenant. |  |  | Sharepoint Administrator / Junior Sharepoint Developer - Resource screening is in progress |  | BCP and Information Security Risk Register not submitted by the project team
New Era Cap | Quality Assurance |  | Staff Aug | T&M | Tower 1 |  |  | Rajeev Kallumpurath | Y | Green | Green | Green | None | 1) B2B Order Approval Release : Critical Path Regression is currently in progress.​ 2) B2B Saved Bag Release : Started with validations​ 3) EMEA Rebound Return : Test planning completed​ 4) Resumed Validations for : Shopify POS Project | 1) B2B Order Approval​ - Complete Critical Path Regression​ 2) Shopify POS - Validation of change requests from SAP​ 3) SOFIA Automation - Add logic to handle for multiple returns against same order​ 4) EMEA Rebound Return - Test execution​ 5) B2B Saved Bag Release - Resume test execution. |  |  |  |  | BCP and Information Security Risk Register not submitted by the project team
New Era Cap | Azure Optimization |  | Staff Aug | T&M | Tower 1 |  |  | Rajeev Kallumpurath | Y | Green | Green | Green | None | Assessments initiative in progress with a target to finish by mid July. Revised pack has been presented to NEC where cost analysis in progress. | Assessments initiative in progress with a target to finish by mid July. |  |  |  |  | BCP and Information Security Risk Register not submitted by the project team
Lending Club | Lending Club |  | Staff Aug | T&M | Tower 1 |  |  | Rajakrishnan S | Y | Green | Green | Green | None | (POD - Alchemy Lending / Sprint-346/ Start date: 27/05/2025 - End date:10/07/2025) a. BOR-4276 - [Web] Fix task flow header and issues reported by UX designer - Issues reported, dev in progress b. BOR-4357, BOR-4358 - Regression R-345 - Completed c. BOR-4359 - Cleansweep account regression issue - Completed d. BOR-4306 - MC routing code cleanup - Completed e. BOR-4310 - [MC API] include new TDL states to user - Issues reported, dev in progress Sprint Tasks: (Deposit POD / Sprint 346 / Release 346 / 27-Jun to 10-Jul) - DEP - 2707 - Increase Resilience in Scheduled Transfers Process Epic - In-progress - DEP - 3246 - RTB: PROD Support and Tech Debt Epic - In-progress - Grooming on Direct Deposit epic Sprint Tasks: (CURE / Sprint 346 / Release 346 / 27-Jun to 10-Jul) - CURE - 1298 - Duplicate email or username validation - In-progress - CURE - 1236 - PLAID fxes for backend error handling - Done Release Tasks: (27-Jun to 02-Jul) - DEP-3460 - Stage regression for R345 - Done Other Tasks: - Daily QA Syncup with LC QA lead on the current project issues and Go/No-Go for R345 - Syncup with PO, Architect, Dev on the ACH Re-design V2 job performance issues reported based my testing. - Syncup with CURE QA and Dev on the issues related to duplicate email or username validation. - Test data along with non-prod config, Miser and admin console support for the offshore team. f. BOR-4356 - [MC] Update BT_DISCOUNT attribute mapping on API - Issues reported, dev in progress g. BOR-4290 – Display TDL/Loan App states to user h. BOR-4373 – Automation for autopay feature i. Created a wiki containing all the pre-product cards visible on member center and Alchemy j. Daily Standup meeting k. Daily QA Meeting POD - Alchemy Deposit / Sprint-346/ Start date: 27/05/2025 - End date:10/07/2025 § DEP-3297– 8 – Scheduled transfers – done – it in testing § DEP-3299 – 13 – Scheduled Transfers – Web development screen. § Sprint grooming meeting happened at Direct Deposit. | a. BOR-4310, BOR-4356, BOR-4276 b. Testing tickets as per requirement Focusing on completing 3299 and planning for Direct Deposit § Any bugs related to Joint owners if any. Next Week (Sprint 346 / Release 346 / 27-Jun to 10-Jul): - Deposits POD - Continuing with in-progress tickets - CURE - Continuing with in-progress tickets | No | NA | Snr Secops-1 (interviews in progress) | Testing Development - Refactoring the existing feature to align with the latest DDS standards, implementing logic changes based on updated Figma designs.
Booster | Booster Staff Aug |  | Staff Aug | Capacity | Tower 2 |  |  | Vijo Jacob | Y | Green | Green | Green | None | Project activities in progress as planned. | Continue with Devops and QA activities. Submit addendum for signature | None |  | None | Execution
Nbora | Zodiac Maritime: D365 Integration |  | Staff Aug | Capacity | Tower 2 |  |  | Vijo Jacob | Y | Green | Green | Green | None | Project activities in progress as planned. | Continue with project activities as per sprint commitments | None |  | None | Execution
GBM | NCSA |  | Managed | Fixed Bid | Tower 2 |  |  | Vijo Jacob | Y | Green | Green | Green | None | Received confirmation on below items to start activities. 1. 5th Service 2. Gate way services 3. Performance and Vulnerability testing | Plan resource for implementation and start discussion with customer on requirements | None |  | Awaiting confirmation on consultant Tirappa for this activitiy | Requirement Gathering
Potentiate Global | Platform1 |  | Staff Aug | Capacity | Tower 2 |  |  | Vijo Jacob | Y | Green | Green | Green | None | CXDEL-1162: Hyundai - Dashboard Access Issue CXDEL-738 :AAAF Daily NPS and Sample Checking Report CXDEL-662 : TFA / TMCA Sales Integration of Sample statistics | CXDEL-802:Toyota - Create comprehensive program alerts CXDEL-1183:Toyota New Comparison Report CXDEL-1175:Toyota Data Supply Quality Salesperson
idDriver | idDriver |  | Managed | T&M | Tower 2 |  |  | Yamunaa Rani | Y | Green | Green | Green | None | EV-34 IDV-Prebook API update | No Tasks | None
Neu Money | Neu Money | Strategic | Managed | T&M | Tower 1 |  |  | Amitha M N | Y | Green | Green | Green |  | UI issue fixing and defect retetsing API updates | UI issue fixing and defect retesting API updates UAT verification Planning for production release | UI isses founnd by Client team during UAT verification -team is fixing that |  | Added Sooraj S R for 1 week. | testing | BCP and Information Security Risk Register not submitted by the project team
Compare Club | Compare Club |  | Staff Aug | T&M | Tower 2 |  |  | Ashwathy Nair | Y | Green | Green | Green | None | * New sprint started for most of the squad * Aswathy S Nath and Hussain received Spot award * Devabala and Faris onboarded in the project * Had a walkthrough on playwright tool with Kunal. Walkthrough of the new test strategy from CC is planned for next week. * Discussion on the bill rate revision is in progress. | * Continuing Sprint task * Discussion with Kunal planned on test strategy | No concern as of now | NA | AMBER - Aswathy John wants to step out of SE Mentor and join reflection. Discussion initiated for the same. | NA
Auto Club Group | AAA Data Minimization | Strategic | Managed | Fixed Bid | Tower 1 |  |  | Prakash S | Y | Green | Green | Green | None | Deployment completed for Development environment and QA has started Initial and table records analysis in progress Incrimental load pipeline in development | QA to be completed Orchestration for Autosys jobs | None |  | None | Execution phase | BCP and Information Security Risk Register not submitted by the project team
Pidilite | Pidilite SaaS Integration Project Phase 2 |  | Managed | Fixed Bid | Tower 1 |  |  | Yamunaa Rani | Y | Green |  |  |  | Retailer Creation and Order creation were signed off, received key vault configuration and Metadata format as part of review for prod deployment. Key Vault configuration is complete. Metadata is in progress. | Production deployment
Novo Cinemas | Novo Cinemas - Qatar AMC |  | Staff Aug | Capacity | Tower 2 |  |  | Yamunaa Rani | Y | Green |  |  |  | API Calls for Loyalty Recognition - resolved email update request - resolved email update request - resolved Delete / Update the account - resolved DOHA BANK ISSUE - resolved Update the email - resolved posters not appearing - resolved
Auto Club Group | AAA Payment Integration Service | Strategic | Managed | Fixed Bid | Tower 1 |  |  | Prakash S | Y | Green | Green | Green | None | Discovery phase is in progress | Discovery to continue Architecture review and aproval process with AAA team | Acces request for newly onboarded team members are pending due to slow response from AAA team |  | Resource will be on boarded as pewr the plan reviewed | Discovery | BCP and Information Security Risk Register not submitted by the project team
AKS Global Support | AKS Global Support |  | Staff Aug | Capacity | Tower 2 |  |  | Yamunaa Rani | Y | Green | Green | Green |  | SOW renewed contract is shared for Client sign off
Bahrain Bourse | BHB AMC support project |  | Staff Aug | Capacity | Tower 2 |  |  | Yamunaa Rani | Y | Green | Green | Green |  | No incidents
New Era Cap | Business Analysts |  | Staff Aug | T&M | Tower 1 |  |  | Rajeev Kallumpurath | Y | Amber | White | White | None | SOW has been closed by 30th June. No Tasks. Team has been released from the account. | No Tasks |  |  |  |  | BCP and Information Security Risk Register not submitted by the project team
CohnReznick | CohnReznick AH Tracker | Strategic | Managed | Fixed Bid | Tower 1 |  |  | Umesh Choudhary | N | Amber | Green | Green | None | Application Architecture​-In Dev​- 98%​ Environment Setup for AH tracker project​ -Blocked ​-95 %​ Data Import & Synchronization​ Dev Blocked​-30%​ RBAC UI+ Backend implementation​ QA Blocked​-95%​ Dashboard and visibility ​-In Dev​-40%​ UI Development -Job Queue​-Done​-100%​ User login using SSO​-QA is Blocked​-95 % ​ Non US based users login​-QA is blocked​-90%​ Remote users login using citrix​-QA is blocked​ -90%​ | Environment Setup for AH tracker project—Will completed pending azure resource deployement​ Data Import & Synchronization-Configuration of SHIR and ADF and ETL development​ Testing- RBAC UI+ Backend implementation​ Dashboard and visibility ( Backend and API integration for dashboard )​ Testing-User login using SSO​ | 1)Most of the development resources have been provisioned, except for the App Service, which is pending due to a quota issue. This is currently blocked due to the dependency on CR and the holiday in the current week 2) QA planned activities is getting delayed due to not deployment of QA environment on Azure. DevOps blocked by CR dependency due to US holidays of 1 weeks |  |  | Development | BCP and Information Security Risk Register not submitted by the project team
Now Health | NOW Health – VAPT |  | Managed | T&M | Tower 2 |  |  | Shanavaz | N |  | White | White
Scope Retail | Scope Retail WMS |  | Staff Aug | Capacity | Tower 1 |  |  | Rajakrishnan S | N | [10 empty] | Not Updated from Last 4 weeks
GBM | MOI DP Implementation |  | Managed | Fixed Bid | Tower 2 |  |  | Vijo Jacob | N | [10 empty] | No activity happening
Note on L1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Current Week
Note on M1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Current Week